CITY OF DULUTH

PURCHASING DIVISION

Room 100 City Hall

411 West First Street

Duluth, Minnesota  55802-1199

218/730-5340 	218/730-5922 FAX

Addendum # 1

13-28DS Demo of 6 Purchase Flood Damaged Parcels

This addendum serves to notify all bidders of additional bid language that is now part of this bid.

Payment and Performance Bonds for 100% of bid amount will be required of successful bidder(s).

---------------------------------------------------------------------------------------------------------------------

Furnish all labor, supervision, permits, equipment, insurance (as per attached requirements), and all else necessary to Demolish the following structures all in accordance with the specifications of the City of Duluth Purchasing Division and the Division of Building Inspections. Also remove any and all accessary buildings on the property unless noted otherwise. As Noted: your bid includes the following:

Disconnect of utilities, demolition, debris removal and clean up, and proper disposal of debris. Thirty working days are allowed to complete each building (No Exceptions). Liquidating damages of 10% of bid value per day past 30 days will be deducted from the bid costs.

The City reserves the right to remove any parcel from this contract which may be removed by owner or may negotiate cleanup of any parcel whole or in part remaining during the like of this contract. Note: New full sized plywood/OBS sheathing covering windows and/or doors must be removed and returned to the downtown Firehall #1. Non-negotiated loss of sheathing shall be considered a deduction of demolition parcel cost.

Strict Requirements:

Bidder must dispose of waste at an approved and certified disposal site. Abatement of asbestos and regulated waste and the stabilization of lead paint will be performed by others. Demolition will not start until asbestos, regulated wast5e and lead paint have been abated and stabilized as required by law.

Absolutely no demolition debris to be used for fill at demolition site.

- Disposal site fro demolition debris:

- _________________________________________________

Location

- Disposal site for asbestos material:

- _________________________________________________

Location

Successful bidder will be required to furnish weight tickets or volume tickets from approved landfill/disposal site for each billing prior to receiving payment. There will be no payments made until this procedure is followed.

Note: Bidders shall indicate all other disposal sites when two (2) or more sites are used. Also Bidder shall indicate the estimated quantities and type material to be disposed of at each of the sites. Failure to do so may be cause for rejection of bid.

The City of Duluth reserves the right to awards this bid on a Total Bid basis or a Low Bid per line item basis.

There are no other changes to this bid.

Please make a copy of this addendum, sign and date and return with your bid.

Thank you.

Dennis Sears. Purchasing Agent.