Copyright 2010 by The American Institute of Architects (AIA)

Exclusively published and distributed by Architectural Computer Services, Inc. (ARCOM) for the AIA

SECTION 01 7700

CLOSEOUT PROCEDURES

Revise this Section by deleting and inserting text to meet Project-specific requirements.

This Section uses the term "Architect."  Change this term to match that used to identify the design professional as defined in the General and Supplementary Conditions.

Verify that Section titles referenced in this Section are correct for this Project's Specifications; Section titles may have changed.

- GENERAL

      - RELATED DOCUMENTS

Retain or delete this article in all Sections of Project Manual.

        - Drawings and general provisions of the Contract, including General and Supplementary Conditions and other Division 01 Specification Sections, apply to this Section.

      - SUMMARY

        - Section includes administrative and procedural requirements for contract closeout, including, but not limited to, the following:

Coordinate list below with "Related Requirements" subparagraphs.

          - Substantial Completion procedures.

          - Final completion procedures.

          - Warranties.

          - Final cleaning.

          - Repair of the Work.

        - Related Requirements:

Retain subparagraphs below to cross-reference requirements Contractor might expect to find in this Section but are specified in other Sections.

          - Section 01 7300 "Execution" for progress cleaning of Project site.

      - ACTION SUBMITTALS

        - Contractor's List of Incomplete Items:  Initial submittal at Substantial Completion.

        - Certified List of Incomplete Items:  Final submittal at Final Completion.

      - CLOSEOUT SUBMITTALS

Revise list below after editing Section Text.

        - Certificates of Release:  From authorities having jurisdiction.

        - Certificate of Insurance:  For continuing coverage.

      - MAINTENANCE MATERIAL SUBMITTALS

        - Schedule of Maintenance Material Items:  For maintenance material submittal items specified in other Sections.

      - SUBSTANTIAL COMPLETION PROCEDURES

        - Contractor's List of Incomplete Items:  Prepare and submit a list of items to be completed and corrected (Contractor's punch list), indicating the value of each item on the list and reasons why the Work is incomplete.

        - Submittals Prior to Substantial Completion:  Complete the following a minimum of 10 days prior to requesting inspection for determining date of Substantial Completion.  List items below that are incomplete at time of request.

          - Certificates of Release:  Obtain and submit releases from authorities having jurisdiction permitting Owner unrestricted use of the Work and access to services and utilities.  Include occupancy permits, operating certificates, and similar releases.

          - Submit closeout submittals specified in other Division 01 Sections, including project record documents, operation and maintenance manuals, final completion construction photographic documentation, damage or settlement surveys, property surveys, and similar final record information.

          - Submit closeout submittals specified in individual Sections, including specific warranties, workmanship bonds, maintenance service agreements, final certifications, and similar documents.

          - Submit maintenance material submittals specified in individual Sections, including tools, spare parts, extra materials, and similar items, and deliver to location designated by Architect.  Label with manufacturer's name and model number where applicable.

Retain "Schedule of Maintenance Material Items" Subparagraph below when documentation of maintenance material item submittal is required for Project.

            - Schedule of Maintenance Material Items:  Prepare and submit schedule of maintenance material submittal items, including name and quantity of each item and name and number of related Specification Section.  Obtain Architect's signature for receipt of submittals.

Retain first subparagraph below when sustainable design submittals are required for Project.

          - Submit changeover information related to Owner's occupancy, use, operation, and maintenance.

        - Procedures Prior to Substantial Completion:  Complete the following a minimum of 10 days prior to requesting inspection for determining date of Substantial Completion.  List items below that are incomplete at time of request.

          - Advise Owner of pending insurance changeover requirements.

          - Make final changeover of permanent locks and deliver keys to Owner.  Advise Owner's personnel of changeover in security provisions.

          - Complete startup and testing of systems and equipment.

          - Perform preventive maintenance on equipment used prior to Substantial Completion.

          - Instruct Owner's personnel in operation, adjustment, and maintenance of products, equipment, and systems.

          - Terminate and remove temporary facilities from Project site, along with mockups, construction tools, and similar elements.

          - Complete final cleaning requirements, including touchup painting.

          - Touch up and otherwise repair and restore marred exposed finishes to eliminate visual defects.

Revise "Inspection" Paragraph below to comply with office policy and Project requirements.

        - Inspection:  Submit a written request for inspection to determine Substantial Completion a minimum of 10 days prior to date the work will be completed and ready for final inspection and tests.  On receipt of request, Architect will either proceed with inspection or notify Contractor of unfulfilled requirements.  Architect will prepare the Certificate of Substantial Completion after inspection or will notify Contractor of items, either on Contractor's list or additional items identified by Architect, that must be completed or corrected before certificate will be issued.

          - Reinspection:  Request reinspection when the Work identified in previous inspections as incomplete is completed or corrected.

          - Results of completed inspection will form the basis of requirements for final completion.

      - FINAL COMPLETION PROCEDURES

        - Submittals Prior to Final Completion:  Before requesting final inspection for determining final completion, complete the following:

Revise subparagraphs below to match the Supplementary Conditions.

          - Submit a final Application for Payment according to Section 012900 "Payment Procedures."

          - Certified List of Incomplete Items:  Submit certified copy of Architect's Substantial Completion inspection list of items to be completed or corrected (punch list), endorsed and dated by Architect.  Certified copy of the list shall state that each item has been completed or otherwise resolved for acceptance.

          - Certificate of Insurance:  Submit evidence of final, continuing insurance coverage complying with insurance requirements.

          - Submit pest-control final inspection report.

Revise "Inspection" Paragraph below to comply with office policy and Project requirements.

        - Inspection:  Submit a written request for final inspection to determine acceptance a minimum of 10 days prior to date the work will be completed and ready for final inspection and tests.  On receipt of request, Architect will either proceed with inspection or notify Contractor of unfulfilled requirements.  Architect will prepare a final Certificate for Payment after inspection or will notify Contractor of construction that must be completed or corrected before certificate will be issued.

          - Reinspection:  Request reinspection when the Work identified in previous inspections as incomplete is completed or corrected.

      - LIST OF INCOMPLETE ITEMS (PUNCH LIST)

        - Organization of List:  Include name and identification of each space and area affected by construction operations for incomplete items and items needing correction including, if necessary, areas disturbed by Contractor that are outside the limits of construction.

          - Organize list of spaces in sequential order.

          - Organize items applying to each space by major element, including categories for ceiling, individual walls, floors, equipment, and building systems.

          - Include the following information at the top of each page:

            - Project name.

            - Date.

            - Name of Architect.

            - Name of Contractor.

            - Page number.

      - SUBMITTAL OF PROJECT WARRANTIES

        - Time of Submittal:  Submit written warranties on request of Architect for designated portions of the Work where commencement of warranties other than date of Substantial Completion is indicated, or when delay in submittal of warranties might limit Owner's rights under warranty.

On advice of Owner's legal counsel, revise "Partial Occupancy" Paragraph below to suit Project.  Sometimes, extended warranties may be necessary.

        - Partial Occupancy:  Submit properly executed warranties within [15] <Insert number> days of completion of designated portions of the Work that are completed and occupied or used by Owner during construction period by separate agreement with Contractor.

        - Organize warranty documents into an orderly sequence based on the table of contents of Project Manual.

Revise first subparagraph below to suit Project.

          - Bind warranties and bonds in heavy-duty, three-ring, vinyl-covered, loose-leaf binders, thickness as necessary to accommodate contents, and sized to receive 8-1/2-by-11-inch (215-by-280-mm) paper.

          - Provide heavy paper dividers with plastic-covered tabs for each separate warranty.  Mark tab to identify the product or installation.  Provide a typed description of the product or installation, including the name of the product and the name, address, and telephone number of Installer.

          - Identify each binder on the front and spine with the typed or printed title "WARRANTIES," Project name, and name of Contractor.

Retain "Warranty Electronic File" Subparagraph below and paper copy documents if required by Owner.  Indexing requirement below can be performed automatically using PDF publishing software.

          - Warranty Electronic File:  Scan warranties and bonds and assemble complete warranty and bond submittal package into a single indexed electronic PDF file with links enabling navigation to each item.  Provide bookmarked table of contents at beginning of document.

Coordinate paragraph below if using Section 017823 "Operation and Maintenance Data."

        - Provide additional copies of each warranty to include in operation and maintenance manuals.

- PRODUCTS

      - MATERIALS

"Cleaning Agents" Paragraph below contains basic requirements.  Revise this article to suit Project or to accommodate unusual situations.

        - Cleaning Agents:  Use cleaning materials and agents recommended by manufacturer or fabricator of the surface to be cleaned.  Do not use cleaning agents that are potentially hazardous to health or property or that might damage finished surfaces.

Requirements in subparagraph below are from the USGBC's "LEED 2009 for Existing Buildings:  Operation & Maintenance" (LEED-EB), Credit IEQ 3.3.  Revise if Owner requirements differ.

          - Use cleaning products that comply with Green Seal's GS-37, or if GS-37 is not applicable, use products that comply with the California Code of Regulations maximum allowable VOC levels.

- EXECUTION

      - FINAL CLEANING

Delete this article if owners prefer to use their own personnel.  Cleaning provisions in the General Conditions are limited to rubbish removal and similar activities.

        - General:  Perform final cleaning.  Conduct cleaning and waste-removal operations to comply with local laws and ordinances and Federal and local environmental and antipollution regulations.

        - Cleaning:  Employ experienced workers or professional cleaners for final cleaning.  Clean each surface or unit to condition expected in an average commercial building cleaning and maintenance program.  Comply with manufacturer's written instructions.

If final cleaning is delayed until final acceptance, revise subparagraph below.

          - Complete the following cleaning operations before requesting inspection for certification of Substantial Completion for entire Project or for a designated portion of Project:

Subparagraphs below are a sample list of final cleaning requirements.  Revise to suit Project.

            - Clean Project site, yard, and grounds, in areas disturbed by construction activities, including landscape development areas, of rubbish, waste material, litter, and other foreign substances.

            - Sweep paved areas broom clean.  Remove petrochemical spills, stains, and other foreign deposits.

            - Rake grounds that are neither planted nor paved to a smooth, even-textured surface.

            - Remove tools, construction equipment, machinery, and surplus material from Project site.

            - Remove snow and ice to provide safe access to building.

            - Clean exposed exterior and interior hard-surfaced finishes to a dirt-free condition, free of stains, films, and similar foreign substances.  Avoid disturbing natural weathering of exterior surfaces.  Restore reflective surfaces to their original condition.

            - Remove debris and surface dust from limited access spaces, including roofs, plenums, shafts, trenches, equipment vaults, manholes, attics, and similar spaces.

            - Sweep concrete floors broom clean in unoccupied spaces.

            - Clean mirrors.  Remove glazing compounds and other noticeable, vision-obscuring materials.  Polish mirrors, taking care not to scratch surfaces.

            - Remove labels that are not permanent.

Revise subparagraphs below to suit Project.  Check for conflict or duplication with provisions in other Sections.

            - Wipe surfaces of mechanical and electrical equipment and similar equipment.  Remove excess lubrication, paint and mortar droppings, and other foreign substances.

            - Clean plumbing fixtures to a sanitary condition, free of stains, including stains resulting from water exposure.

            - Clean light fixtures, lamps, globes, and reflectors to function with full efficiency.

            - Leave Project clean and ready for occupancy.

"Pest Control" and "Construction Waste Disposal" paragraphs below represent end of the Work specified in Section 015000 "Temporary Facilities and Controls." Most projects require these actions at completion of construction.  Insert a paragraph on termite inspection where required by authorities having jurisdiction or applicable for Project.

        - Construction Waste Disposal:  Comply with waste disposal requirements in Section 01 7419 "Construction Waste Management and Disposal."

Insert an article on continuing inspections or consultations by Contractor if required.  Possibly insert a schedule of approximate times for inspections.

      - REPAIR OF THE WORK

        - Complete repair and restoration operations before requesting inspection for determination of Substantial Completion.

        - Repair or remove and replace defective construction.  Repairing includes replacing defective parts, refinishing damaged surfaces, touching up with matching materials, and properly adjusting operating equipment.  Where damaged or worn items cannot be repaired or restored, provide replacements.  Remove and replace operating components that cannot be repaired. Restore damaged construction and permanent facilities used during construction to specified condition.

          - Remove and replace chipped, scratched, and broken glass, reflective surfaces, and other damaged transparent materials.

          - Touch up and otherwise repair and restore marred or exposed finishes and surfaces.  Replace finishes and surfaces that that already show evidence of repair or restoration.

            - Do not paint over "UL" and other required labels and identification, including mechanical and electrical nameplates.  Remove paint applied to required labels and identification.

          - Replace parts subject to operating conditions during construction that may impede operation or reduce longevity.

          - Replace burned-out bulbs, bulbs noticeably dimmed by hours of use, and defective and noisy starters in fluorescent and mercury vapor fixtures to comply with requirements for new fixtures.

Insert additional requirements to suit Project.

END OF SECTION 01 7700