{"text_format":"1","workbook":"xlsx","n_sheets":1,"sheets":["blank form"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":2,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"blank form","index":0,"n_rows":154,"n_cols":22,"rows_kept":154,"cut":false,"hidden":false,"merged":[[4,0,6,0],[0,1,0,5],[1,0,1,14]]}
["Kraus-Anderson® Construction ",null,null,null,null,null,null,null,null,"Three Week Look Ahead Schedule "]
["KACC Project #20225  New Passenger Terminal Bid Package I"]
[]
[]
["Contractor","Sun","Mon","Tue","Wed","Th","Fri","Sat","Sun","Mon","Tue","Wed","Th","Fri","Sat","Sun","Mon","Tue","Wed","Th","Fri","Sat"]
[null,"Aug","Aug","Aug ","Sept","Sept","Sept","Sept","Sept","Sept","Sept","Sept","Sept","Sept","Sept","Sept","Sept","Sept","Sept","Sept","Sept","Sept"]
[null,29,30,31,1,2,3,4,5,6,7,8,9,10,11,12,13,14,15,16,17,18]
["Division 1 - General Requirements"]
["Kraus-Anderson Construction"]
[" - Construction meeting"]
[" - Foreman's meeting"]
[" - Site coordination"]
[]
[]
[]
["Testing"]
["American Engineering Testing, Inc."]
[]
[]
[]
[]
[]
[]
["WS 2.10 Civil & Site Electrical"]
["Northland Constructors"]
["Phase 1"]
[]
[" "]
[]
[" - Pedestrian Fencing"]
[" - Remove Lights & Bases"]
[" - Traffic Control Signage"]
[" - Build Temp Rd. East"]
["OPEN H.C. LOT & TEMP RD EAST"]
[" - Install Crossover @ S.W. Parking Area"]
["Phase 2A"]
[]
[" -Close Exist Short Term Lot"]
[" -Asphalt Removal"]
[" -Install Utilities"]
[" - Utility Removals"]
["West Temp Road"]
[]
["Electrical"]
["APi Electric"]
[" - Install Construction Lighting"]
[" - Access Controls for Tunnel"]
[" - Electrical at Employee Access Road area"]
[" - Site Electrical Work Lower Grinden Dr. (west)"]
["Sub Grade Elect. Piping"]
["Concrete & Bitiminous Sawing"]
["Concrete Sawing Services"]
[" - Saw Cut Asphalt & Concrete"]
[]
[]
[]
["Landscaping & Erosion Control"]
["Erosion Control Specialists, Inc."]
[]
[]
[]
[]
[]
["Fill and Abandon Pipe"]
["EJM Pipe Service, Inc."]
[]
[]
[]
[]
[]
["Directional Boring"]
["Ground Effects Directional Boring"]
[]
[]
[]
[]
[]
["Concrete Flatwork"]
["Hovland, Inc."]
[" - Handicap Lot Curb Ramp"]
[]
[]
[]
[]
["Fencing/Guardrail"]
["Keller Fence Company"]
[" - Temp Construction Fencing"]
[" - Remove Guard Rail and cut off posts"]
[]
[]
["Gas Main"]
["Midwest Boring & Underground"]
[]
[]
[]
[]
[]
["Traffic Markings, Paint, Sealcoat"]
["Sinnott Blacktop, Inc."]
[" - Handicap Lot Striping Complete"]
[]
[]
[]
[]
["Tree Removal"]
["Rick's Tree Service"]
["Complete"]
[]
[]
[]
[]
["CIPP Liner"]
["Veit Specialty Contracting"]
[" - Sanitary lining"]
[]
[]
[]
[]
["Concrete Waterproofing"]
["Waterproofing by Experts, Inc."]
[]
[]
[]
["WS 3.10 Structural Concrete"]
["Kelleher Construction, Inc."]
[]
[]
[]
["Rebar Installation"]
["Woody's Rebar Co., Inc."]
[]
[]
[]
[]
["WS 4.10 Masonry"]
["Harbor City Masonry, Inc."]
[]
[]
[]
[]
[]
["WS 5.10 Structural/Miscellaneous Steel"]
["Dynamic Structural Steel LLC"]
[]
[]
[]
[]
["Steel Erector"]
["Northern Industrial Erectors, Inc."]
[]
[]
[]
[]
["K.A. Miscellaneous Walkways"]