{"text_format":"1","workbook":"xlsx","n_sheets":1,"sheets":["blank form"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":2,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"blank form","index":0,"n_rows":160,"n_cols":22,"rows_kept":160,"cut":false,"hidden":false,"merged":[[4,0,6,0],[0,1,0,5],[1,0,1,14]]}
["Kraus-Anderson® Construction ",null,null,null,null,null,null,null,null,"Three Week Look Ahead Schedule "]
["KACC Project #20225  New Passenger Terminal Bid Package I"]
[]
[]
["Contractor","Sun","Mon","Tue","Wed","Th","Fri","Sat","Sun","Mon","Tue","Wed","Th","Fri","Sat","Sun","Mon","Tue","Wed","Th","Fri","Sat"]
[null,"Sept","Sept","Sept","Sept","Sept","Sept","Sept","Sept","Sept","Sept","Sept","Sept","Sept","Sept","Sept","Sept","Sept","Sept","Sept","0ct.","Oct."]
[null,12,13,14,15,16,17,18,19,20,21,22,23,24,25,26,27,28,29,30,1,2]
["Division 1 - General Requirements"]
["Kraus-Anderson Construction"]
[" - Construction meeting"]
[" - Foreman's meeting"]
[" - Site coordination  ( On Going)"]
[]
[]
[]
["Testing"]
["American Engineering Testing, Inc."]
["As needed"]
[]
[]
[]
[]
[]
["WS 2.10 Civil & Site Electrical"]
["Northland Constructors"]
[]
[" - Pedestrian Fencing"]
[]
[" - Traffic Control Signage"]
[" - EAST Pedestrian Path and Tunnel  Closure"]
["  close 6:ooam on 17th to end of day 21st"]
[]
[]
[]
[" -Sub Cut Temp road and Parking (west)"]
[" - Granular and Class 5 (West)"]
[]
[" - WEST Close 1/2 EXIST Grinden Dr at Tie in Area"]
[" - Open 1/2 and close the other 1/2 West Tie In Area"]
[" - 3:00AM Pave Temp tie in WEST and Temp Rd. also East Ped. Path area"]
[" - Open East Tunnel And Ped. Path (Late Day)"]
[" - Start digging AA line Canopy Footings"]
[" - Start Center Utilities "]
[" - Close West Tunnel for 3 wks.  Option 1"]
[" - Option 2 = Oct. 5th. for 3 wks. If Option 1 Not ready"]
[" - Dig Bldg. Footings"]
[]
[]
["Electrical"]
["APi Electric"]
[" "]
[" - Access Controls for Tunnel  (complete)"]
[]
[" - Site Electrical Work Lower Grinden Dr. (west)"]
["Sub Grade Elect. Piping As Needed"]
["Concrete & Bitiminous Sawing"]
["Concrete Sawing Services"]
[" - Saw Cut Asphalt & Concrete"]
[]
[]
[]
["Landscaping & Erosion Control"]
["Erosion Control Specialists, Inc. (As Needed)"]
[]
["20199 Landscaping"]
[]
[]
[]
["Fill and Abandon Pipe"]
["EJM Pipe Service, Inc."]
[]
[]
[]
[]
[]
["Directional Boring"]
["Ground Effects Directional Boring"]
[]
[]
[]
[]
[]
["Concrete Flatwork"]
["Hovland, Inc."]
[]
[]
[]
[]
["Fencing/Guardrail"]
["Keller Fence Company"]
[" - Temp Construction Fencing"]
[]
[]
[]
["Gas Main"]
["Midwest Boring & Underground"]
["Install gas main"]
[]
[]
[]
[]
["Traffic Markings, Paint, Sealcoat"]
["Sinnott Blacktop, Inc."]
[" - Handicap Lot Striping Complete"]
[]
[]
[]
[]
["Tree Removal"]
["Rick's Tree Service"]
["Complete"]
[]
[]
[]
[]
["CIPP Liner"]
["Veit Specialty Contracting"]
[" - Sanitary lining"]
[]
[]
[]
[]
["Concrete Waterproofing"]
["Waterproofing by Experts, Inc."]
[]
[]
[]
["WS 3.10 Structural Concrete"]
["Kelleher Construction, Inc."]
["Canopy footings & Piers at AA Line"]
["Bldg. Footings West End"]
[]
["Rebar Installation"]
["Woody's Rebar Co., Inc."]
["Install Rebar @ Canopy Footings &Piers at AA Line"]
[]
[]
[]
["WS 4.10 Masonry"]
["Harbor City Masonry, Inc."]
[]
[]
[]
[]
[]
["WS 5.10 Structural/Miscellaneous Steel"]
["Dynamic Structural Steel LLC"]
[]
[]
[]
["Steel Erector"]
["Northern Industrial Erectors, Inc."]
[]
[]
[]
[]
["K.A. Miscellaneous Walkways"]
[]
[]
["NOTES:"]