{"text_format":"1","workbook":"xlsx","n_sheets":1,"sheets":["blank form"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":2,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"blank form","index":0,"n_rows":192,"n_cols":22,"rows_kept":192,"cut":false,"hidden":false,"merged":[[4,0,6,0],[0,1,0,5],[1,0,1,14]]}
["Kraus-Anderson® Construction ",null,null,null,null,null,null,null,null,"Three Week Look Ahead Schedule "]
["KACC Project #20225  New Passenger Terminal Bid Package I"]
[]
[]
["Contractor","Sun","Mon","Tue","Wed","Th","Fri","Sat","Sun","Mon","Tue","Wed","Th","Fri","Sat","Sun","Mon","Tue","Wed","Th","Fri","Sat"]
[null,"Oct","Oct","Oct","Oct","Oct","0ct","Oct","Oct","Oct","Oct","Oct","Oct","Oct","Oct","Oct","Oct","Oct","Oct","Oct","Oct","Oct"]
[null,10,11,12,13,14,15,16,17,18,19,20,21,22,23,24,25,26,27,28,29,30]
["Division 1 - General Requirements"]
["Kraus-Anderson Construction"]
[" - Construction meeting"]
[" - Foreman's meeting"]
[" - Site coordination  (On Going)"]
[]
[]
[]
["Testing"]
["American Engineering Testing, Inc."]
["As needed"]
[]
[" "]
["Braun  "]
[" - Compaction, Rebar, Conc."]
[]
["WS 2.10 Civil & Site Electrical"]
["Northland Constructors"]
[" - Traffic Control Signage  (As Needed)"]
[" - Dig A. & A-1 line canopy footings"]
[" - Close West Tunnel for 3 wks.  "]
[]
[" - West Tunnel Area Utilities Complete"]
[" - Build West Parking & Temp Tunnel Access"]
[" - Dig Bldg. Footings, Sub Cuts"]
[" - Patch paving where duct bank & utilities cross east & west end Ped Path"]
[" -  Subcut & Build East Parking   "]
[" - Curb and Gutter East /West Parking (TBD)"]
[" - Center Bldg. Area Utilities and Site Utilities"]
[" - Install Drain Tile"]
[]
[" - Start backfilling"]
[" - Subcut & Build Grinden Drive West to East"]
[" - Install Water Main across Ped Path East"]
[" - Pave West Ped Path"]
[]
[]
["Electrical W.S. 16.10"]
["APi Electric"]
[" - Site Electrical Work Lower Grinden Dr. (west)"]
[" - Site Light Bases and Piping East & West "]
[" - Install Electrical Man Hole, Conduits,Transformer Pad, Duct Bank, @ East Parking Area"]
[" - Install Communication Man Hole,Conduits @ East Parking Area"]
[" - Install duct bank across East ped path"]
[" - Misc Site Work"]
[]
[]
["Concrete & Bitiminous Sawing"]
["Concrete Sawing Services"]
[" - Saw Cut Asphalt & Concrete"]
[" - Complete"]
[]
[]
["Landscaping & Erosion Control"]
["Erosion Control Specialists, Inc. "]
[" - Seeding and Blanket as needed"]
[]
[]
[]
["AJ's Landscaping"]
["20199 Landscaping"]
[]
[]
[]
["Fill and Abandon Pipe"]
["Cellular Concrete"]
[" - Complete"]
[]
[]
[]
["Directional Boring"]
["Ground Effects Directional Boring (behind Hertz)"]
[" - Complete"]
[]
[]
[]
["Concrete Flatwork"]
["Hovland, Inc."]
[" - Curb and Gutter (TBD)"]
[]
[]
[]
["Fencing/Guardrail"]
["Keller Fence Company"]
[" - Temp Construction Fencing"]
[" - Permanent Fence (TBD) waiting for resubmittal"]
[]
[]
["Gas Main"]
["Midwest Boring & Underground"]
[" - Install gas main week of 27th 2-days - complete except for riser to building"]
[]
[]
[]
[]
["Traffic Markings, Paint, Sealcoat"]
["Sinnott Blacktop, Inc.  H.C. Black Out"]
[]
[]
[]
[]
[]
["Tree Removal"]
["Rick's Tree Service"]
[" - Complete"]
[]
[]
[]
[]
["CIPP Liner"]
["Veit Specialty Contracting"]
[" - Sanitary lining"]
[]
[]
[]
[]
["Concrete Waterproofing"]
["Waterproofing by Experts, Inc."]
[" - Foundation Wall Waterproofing Starting @ West"]
[" - Foundation Wall Waterproofing as needed"]
[]
["WS 3.10 Structural Concrete"]
["Kelleher Construction, Inc."]
[" - Bldg. Footings and Column Pads"]
[" - Foundation Walls and Piers"]
[" - Canopy Footings and Piers "]
[]
[]
[]
["Rebar Installation"]
["Woody's Rebar Co., Inc."]
[" - Install Rebar @ Canopy Footings & Piers (TBD)"]
[" - Install Rebar at Bldg.and Column Footings"]
[" - Tie Walls and Piers"]
[]
["WS 4.10 Masonry"]
["Harbor City Masonry, Inc."]
[]
[]
[]
[]
[]
["WS 5.10 Structural/Miscellaneous Steel"]
["Dynamic Structural Steel LLC"]
[" - Delivery tentatively Nov. 1st"]
[]
[]
["Steel Erector"]
["Northern Industrial Erectors, Inc."]
[" - Tentative start Nov. 1st"]
[]
["WS 5.11 Metal Framing"]
["Minuti-Ogle, Inc.  (TBD)"]
[]
[]
[]
["WS 7.10 Metal Panels"]
["The Jamar Company  (TBD)"]
[]
[]
[]
["WS 7.11 EPDM Roof   (TBD)"]
["The Jamar Companhy"]
[]
[]
[]
["WS 8.10 Curtain Wall"]
["Harmon, Inc.     (TBD)"]
[]
[]
[]
["15.10 Mechanical (Below Grade)"]
["A.W. Kuettel & Sons, Inc."]
[" - Storm at canopy areas"]
[" - Sewer, storm, gas mains into building West end"]
[" - Interior storm piping at entries"]
[]
[]
[]
["K.A. Miscellaneous Walkways"]
[" - Build Temp Ped Enclosure"]
[]
["NOTES:"]
[" 1. Call City of Duluth for Inspections."]
[" 2. Let KA.,RS&H, DAA  Know in writing about any Shut Downs or outages. 7 Days in Advance."]