{"text_format":"1","workbook":"xlsx","n_sheets":1,"sheets":["blank form"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":2,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"blank form","index":0,"n_rows":184,"n_cols":22,"rows_kept":184,"cut":false,"hidden":false,"merged":[[4,0,6,0],[0,1,0,5],[1,0,1,14]]}
["Kraus-Anderson® Construction ",null,null,null,null,null,null,null,null,"Three Week Look Ahead Schedule "]
["KACC Project #20225  New Passenger Terminal Bid Package I"]
[]
[]
["Contractor","Sun","Mon","Tue","Wed","Th","Fri","Sat","Sun","Mon","Tue","Wed","Th","Fri","Sat","Sun","Mon","Tue","Wed","Th","Fri","Sat"]
[null,"Nov","Nov","Nov","Nov","Nov","Nov","Nov","Nov","Nov","Nov","Nov","Nov","Nov","Nov","Nov","Nov","Nov","Dec","Dec","Dec","Dec"]
[null,14,15,16,17,18,19,20,21,22,23,24,25,26,27,28,29,30,1,2,3,4]
["Division 1 - General Requirements"]
["Kraus-Anderson Construction"]
[" - Contract Status meetings"]
[" - Construction meeting"]
[" - Site coordination  (On Going)"]
[]
["Testing"]
["American Engineering Testing, Inc."]
["As needed"]
[]
["Braun  Intertec"]
[" - Compaction, Rebar, Conc."]
[]
["WS 2.10 Civil & Site Electrical"]
["Northland Constructors"]
[" - Traffic Control Signage  (As Needed)"]
["  - WEST 1/2 BLDG & SITE"]
[]
[" - Drain Tile and Backfill at Interior & Exterior"]
[]
[" - Final grading , seed & cover"]
[" - CANOPY A-A.1 LINE"]
[" - Dig Canopy Footings grid 8-12 (Only Dug 4 of 7)"]
[]
[" -  EAST 1/2 BLDG & SITE"]
[]
[" -  Install New temp Access into Bldg. Site( as needed)"]
[" - Sub Cut, Sand and Class 5 East Parking (Complete)"]
[" - Continue Digging Bldg. Footings and Pads as needed"]
[]
[" - Switch over Vechicle Traffic to East side of Ped Enclosure  (complete)"]
[]
[" - Drain Tile and Backfill at Interior & Exterior"]
[" - Storm and Water Main Work East Parking (Complete)"]
[]
[" - Final grading , seed & cover"]
[" - PAVING "]
[" -  East/ West Grinden Dr.  ( Next Year)"]
[" -  Pave East Permit Parking Lot  11-8-10"]
[]
[]
[]
[]
[" -  Pave Lower Access Rd. Tie In  11-8-10"]
[]
["Electrical W.S. 16.10"]
["APi Electric"]
[" - WEST"]
[" - Site Electrical Work Lower Grinden Dr. & Parking"]
["  (Sub Grade Complete)"]
[" - EAST"]
[" - Install Electrical Man Hole, Conduits,Transformer Pad, Duct Bank, @ East Parking Area"]
[" - Install Communication Man Hole,Conduits @ East Parking Area"]
[" - Site Elect.  Subgrade Conduits, Light Bases etc."]
[" - Install Lighting& Camera's at Ped Enclosure West"]
["Concrete & Bitiminous Sawing"]
["Concrete Sawing Services"]
[" - Saw Cut Asphalt & Concrete"]
[" - Complete"]
[]
[" - Temp Power into Building"]
["Landscaping & Erosion Control"]
["Erosion Control Specialists, Inc. "]
[" Get site open dirt areas covered up for winter"]
[]
[]
["AJ's Landscaping"]
["20199 Landscaping"]
[]
["Directional Boring"]
["Ground Effects Directional Boring (behind Hertz)"]
[" - Complete"]
[]
[]
["Concrete Flatwork"]
["Hovland, Inc."]
[" - Curb and Gutter at West Lower Access Rd. Tie In"]
[]
[]
[]
["Fencing/Guardrail"]
["Keller Fence Company"]
[" - Temp Construction Fencing"]
[" - Permanent Fence (TBD) waiting for resubmittal"]
[]
[]
["Gas Main"]
["Midwest Boring & Underground"]
["Redo gas main Riser"]
[]
[]
["Traffic Markings, Paint, Sealcoat"]
[" - Stripping at East Employee Parking Lot  11-9-10"]
[]
[]
[]
["CIPP Liner"]
["Veit Specialty Contracting"]
[" - Sanitary lining"]
[]
[]
[]
["Concrete Waterproofing"]
["Waterproofing by Experts, Inc."]
[" - Foundation Wall Waterproofing  As Needed"]
[]
[]
["WS 3.10 Structural Concrete"]
["Kelleher Construction, Inc."]
[" - Bldg. Footings and Column Pads"]
[" - Foundation Walls and Piers"]
[" - Canopy Footings and Piers  A-A.1 line"]
[]
[]
[]
["Rebar Installation"]
["Woody's Rebar Co., Inc."]
[" - Install Rebar @ Canopy Footings & Piers "]
[" - Install Rebar at Bldg.and Column Footings"]
[" - Tie Walls and Piers"]
[]
[]
["WS 4.10 Masonry"]
["Harbor City Masonry, Inc."]
[" - TBD"]
[]
[]
[]
[]
["WS 5.10 Structural/Miscellaneous Steel"]
["Dynamic Structural Steel LLC"]
[" - Deliver Steel to Site"]
[]
["Steel Erector"]
["Northern Industrial Erectors, Inc."]
[" - Start Steel Erection West to East"]
[]
[]
[]
["WS 5.11 Metal Framing"]
["Minuti-Ogle, Inc. "]
[" - (TBD)"]
[]
[]
["WS 7.10 Metal Panels"]
["The Jamar Company"]
[" - (TBD)"]
[]
[]
["WS 7.11 EPDM Roof   "]
["The Jamar Company"]
[" - (TBD)"]
[]
[]
["WS 8.10 Curtain Wall"]
["Harmon, Inc.     "]
[" - (TBD)"]
[]
[]
[" - Crane on site & boom erection"]
[]
["15.10 Mechanical (Below Grade)"]
["A.W. Kuettel & Sons, Inc."]
[" -  West Storm at canopy areas  (Complete)"]
[" -  Gas Main into building West end"]
[" - Storm drains at east side"]
[" - Install Water Main into West end BLDG. "]
[]
[]
[]
["K.A. Miscellaneous Walkways"]
[]
[" - Build  West Temp Ped Enclosure"]
[]
["NOTES:"]
[" 1. Call City of Duluth for Inspections."]
[" 2. Let KA.,RS&H, DAA  Know in writing about any Shut Downs or outages. 7 Days in Advance."]